## Reversion History (hidden)
Revision History
The Revision History table below provides a record of revisions made to this document. Updates are tracked by date the revisions were made, who made the change, a brief description of the changes made, and reason.
Date | Modifier | Change Description/ Reason
2025-10-29 | Services COE | Creation and Launch
2025-01-30 | Services COE | Added Training

## Lists (hidden)
Track | Status | Priority | Color | Type | Threshold Matrix |  |  | Status | Meaning / When to Use
LMS | New | Low | Red | Action | Red | Green | 80% | New | Issue or request just logged; not yet reviewed or assigned.
EPM | In Progress | Medium | Yellow | Question | Yellow | Red | 50% | In Review / Triage | Under initial investigation to confirm scope, impact, or owner.
SMP | Closed | High | Green | Issue | Green | Amber | 70% | In Progress | Actively being worked on by support or technical team.
COMP | Future/On Hold |  |  | Risk | Not Started | Green | 100% | Pending Vendor / External Team | Waiting on third-party or vendor resolution (e.g., Cornerstone support, integration partner).
Technical | [7 empty] | Pending Business Input | Awaiting confirmation or additional info from business users.
General | [7 empty] | Pending Validation / Testing | Fix or configuration applied and awaiting UAT confirmation.
Recruiting | [7 empty] | Resolved | Issue fixed and verified internally, pending formal closure.
[8 empty] | Closed | Fully validated and signed off by business; no further action needed.
[8 empty] | Deferred / Backlog | Not a go-live blocker; to be handled after hypercare period.
[8 empty] | Cancelled / Duplicate | Invalid or duplicate entry; no action required.
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
| #REF! | #REF!
Risk | Not Started | Low | Yes
Issue | On Hold | Med | No
Action | Closed | High
Decision
Priority | Definition
Low | Task or issue has minimal impact on project objectives or deadlines. Can be scheduled after higher-priority items.
Medium | Task or issue is important and should be addressed soon, but a short delay won’t critically impact the project.
High | Task or issue is critical to the project’s success or timeline. Immediate attention is required.

## Executive Summary
Portfolio Manager |  | Yudhistir Saxena (ysaxena@csod.com) |  |  | RAID LOG | High | Medium | Low | Total | % Of Total
Project Manager |  | Ankit Garg (ankitgarg@csod.com) |  |  | Complete | 0 | 0 | 0 | 0 | #DIV/0!
Strategic Integration Manager |  |  |  |  | Closed-Pending Review | 0 | 0 | 0 | 0 | #DIV/0!
Business Consultant |  |  |  |  | In Progress | 0 | 0 | 0 | 0 | #DIV/0!
Technical Consultant |  | Jeeva R ( jeeva.r@vithiit.com) |  |  | Behind | 0 | 0 | 0 | 0 | #DIV/0!
Technical Consultant |  |  |  |  | Not Started | 0 | 0 | 0 | 0 | #DIV/0!
Overall Project Status |  | Green |  |  | Total | 0 | 0 | 0 | 0
Current Date |  | 2026-04-08 |  |  | % Of Total | #DIV/0! | #DIV/0! | #DIV/0!
Accomplishments This Period
Goals / Actions Next Period
Project Path |  |  |  | Green |  | Technical Projects |  |  |  | Green
Milestone Title | Target Start | Target End | Completion | Status |  | Title | Target Start | Target End | Completion | Status
Plan | Feb 2nd Week |  |  |  |  | Single Sign On (SSO) Pilot
Advise | Feb 3rd Week |  |  |  |  | Master Data Load (MDLL) Pilot
Design - Pilot / Sandbox | March 1st Week |  |  |  |  | Historical Data Load (HDLL) Pilot
User Acceptance Testing (In Pilot/Sandbox) | March 4th Week |  |  |  |  | DKIM
Launch - Production Build ¦ Go Live Ready | April 1st Week |  |  |  |  | Single Sign On (SSO) Prod
Hypercare | April 3rd Week |  |  |  |  | Master Data Load (MDLL) Prod
Historical Data Load (HDLL) Prod

## Performance Agenda (hidden)
Topic # | Track | Phase | Session Date & Time | High End Hours | Low End Hours | Average Hours | Attendees | Topics | Agenda | Training Titles | Notes
1 | Performance Implementation | Plan | 2026-03-24 | 1 | 1 | 1 | Cornerstone : PM, BC, TC, SC, PO Customer: Executive Sponsor (ES), Project Manager (PM), System Administrator (SA), Technical Lead (TL), Change Manager (CM), Business Process Owners (BPO) | Kickoff & Team Introductions | Implementation Kick-off Meeting to align stakeholders on project goals, scope, methodology, roles, timeline, and next steps, ensuring clarity and readiness for successful execution.
2 | Technical / Integration Projects | Plan | [Insert Date] | 1 | 0.5 | 0.75 | Cornerstone : TC Customer: System Administrator (SA), Technical Lead (TL), Business Process Owners (BPO) | Technical Kick Off | Review technical projects in scope, confirm methodology, validate timelines, and align on goals to ensure clarity and consistency across all deliverables for Cornerstone and the Customer.
3 | Performance Implementation | Advise | [Insert Date] | 1 | 1 | 1 | Cornerstone : BC Customer: System Administrator (SA), Business Process Owners (BPO) | Discovery | Review current and future state of processes
4 | Performance Implementation | Design | [Insert Date] | 1 | 2 | 1.5 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Baseline System Review | BASELINE IN CUSTOMERS PILOT PORTAL Portal will reflect considerations and use cases learned during the discovery process.
5 | Backend Configuration Review (Optional) | Design | [Insert Date] | 1 | 0.5 | 0.75 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Backend Configuration Review | Review backend system configurations that control how the module functions, this step is optional, default settings would get applied if preference is to skip
6 | Admin Workshop 1 | Design | [Insert Date] | 1 | 0.5 | 0.75 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Admin Workshop | Supplementary Admin Workshops to the online module training, any usecases or queries can be discussed and clarified Focus will be on admin creation of the Performance Sections, Tasks, Task Management | https://cornerstoneu.csod.com/ui/lms-learning-details/app/curriculum/049ff173-ef40-4311-a8de-b8df7d9bed9a
7 | Admin Workshop 2 | Design | [Insert Date] | 1 | 0.5 | 0.75 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Admin Workshop | Supplementary Admin Workshops to the online module training, any usecases or queries can be discussed and clarified Focus will be on end user accessibility of Goals and Performance Tasks | https://cornerstoneu.csod.com/ui/lms-learning-details/app/curriculum/049ff173-ef40-4311-a8de-b8df7d9bed9a
8 | Reporting Workshop | Design | [Insert Date] | 1 | 0.5 | 0.75 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Reporting Workshop | Supplementary Reporting Workshops, any usecases or queries can be discussed and clarified Focus will be on standard reports and reporting 2.0 custom reports | https://help.csod.com/help/csod_0/Content/User/Reporting_Overview.htm
9 | UAT | UAT | [Insert Date] | 0.5 | 0.5 | 0.5 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | UAT Planning Workshop | Define UAT, review testing types, outcomes and logistics, uat prep
10 | UAT | UAT | [Insert Date] | 0.5 | 0.5 | 0.5 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | UAT Check In Sessions | Weekly sessions until UAT is complete Begin UAT, Conduct Testing, Review Issues Log, Questions, etc.
11 | Go-Live | Deliver | [Insert Date] | 0.5 | 0.5 | 0.5 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Go-Live Preparations | Weekly sessions until Go-Live is complete Final modifications, queries etc.
12 | Post Go-Live | Hypercare | [Insert Date] | 0.5 | 0.5 | 0.5 | Cornerstone: BC, SC Customer: System Administrator (SA), Business Process Owners (BPO) | Hypercare ¦ Post Implementation Workshops | Ongoing support provided for Post Go-Live issues for 2 weeks post Go-Live date

## Performance Milestones
Milestones
Week | Milestone/Task | Session | Agenda/Notes | Notes
Project Initiation
| 0 | Kickoff & Team Introductions | Review Organization Units & User Concepts in Cornerstone
| 0 | Discovery | Review current and future state of processes
| 0 | Schedule Recurring Workshops | Schedule recurring weekly calls and other in scope workshops
Core & Data Configurations
| 0 | OU/User Workshop | ORGANIZATIONAL UNITS Review Organization Units & User Concepts in Cornerstone
| 0 | Welcome Page/Learner Home/Branding | SYSTEM BRANDING Introduction to system brand features
| 0 | Navigation Tabs and Links | CORE CONFIGURATION Navigate through system concepts and core preference settings
| 0 | Universal Profile | UNIVERSAL PROFILE Navigate through universal profile preferences and configure decisions
| 0 | Mobile | MOBILE Review Mobile Preferences and Configurations
| 0 | Skills and Capabilities | Skills & Capabilities Review Capability Models, Custom Skills and People Matrix This topic cannot be covered unti there is valid OU and User Data Loaded to the portal.
Consulting: Sprint 1
| 0 | Configure Goals | GOALS Goal Prefernces, Goal Configuration, Goals Library and Goals Perspective/Categories
| 0 | Build Comptency Bank, Models and Assessments | PERFORMANCE MANAGEMENT Comptency Assessmetn Bank, Competency Assessment Models, Competency Assessment Tasks
| 0 | Create Observation Checklists | PERFORMANCE MANAGEMENT Create and manage performance observation checklists
| 0 | Configure Development Plans | DEVELOPMENT PLANS Activity Types, Custom Fields, Development Plan Preferences, Objective Categories, Plan Categories, Plan Templates
| 0 | Update Performance Review Print View | PERFORMANCE REVIEWS Set Printable View
Consulting: Sprint 2
| 0 | Create Performance Review Sections and Define Rating Scale | PERFORMANCE REVIEWS Form Sections, Comment Assistant
| 0 | Create Performance Review Tasks: Standard | PERFORMANCE REVIEWS Task Categories and Standard Tasks
| 0 | Create Performance Review Tasks: Off Cycle | PERFORMANCE REVIEWS Off Cycle Tasks
| 0 | Check-Ins | CHECK-INS Check-Ins Template and Home Page Customization
| 0 | Feedback | CONFIGURATION TOOLS > CORE FUNCTIONS > UNIVERSAL PROFILE > GENERAL PREFERENCES Define preferences for Feedback, by Division
Consulting: Sprint 3
| 0 | Emails | CORE FUNCTIONS EMAIL MANAGEMENT / EMAIL DIGEST MANAGMENT Create and manage email content and settings for activity-driven messages. Create and manage email digest content and settings for periodic messages
| 0 | Security Roles | CORE FUNCTIONS / SECURITY ROLE ADMINISTRATION
| 0 | Reporting | REPORTS / STANDARD / REPORTING 2.0 / DASHBOARDS
Validation and Testing
| 0 | Kickoff & Process Review | Kick Off UAT and review Scripts
| 00/01/1900 - 00/01/1900 | Active Testing | Begin UAT, Conduct Testing, Review Issues Log, Questions, etc.
| 0 | Testing Completion | • Execute communication/marketing plan • Review Configuration Checklist / Open Items • Review System Readiness for Go-live (Production Configuration/Completeness)
Project Wrap Up
| 0 | Go-Live Resource Review
| 1900-01-05 | Implementation to Support Transition
| 1900-01-12 | Project Complete
Formulas:
Milestone/Task = WORKDAY([Milestone/Task, row above],5)
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Goes into the Edge Project

## Performance Planner
Task | Description | Duration | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Owner | Status | Yes Prep Comments
Performance Implementation | [6 empty] | All
Project Kick Off | Officially start the project with all stakeholders; review scope, roles, and timelines. | 0 |  |  |  |  | Project Manager | To be started
Discovery - Questionnaire | Gather initial inputs on current performance processes and expectations. | 0 |  |  |  |  | Project Manager | To be started
Success Centre Access and Trainings Review | Ensure client has access to Cornerstone resources and training materials. | 15 |  |  |  |  | Customer | To be started
Share updated questionnaire | Customer will complete quiestionnaire and provide any document to help understand current processes and needs | 0 |  |  |  |  | Customer | To be started
Discovery Workshop Session | Discuss business needs and validate requirements for Performance setup. | 0 |  |  |  |  | Business Consultant | To be started
OU Work shop | Organisation Unit Workshop | 0 |  |  |  |  | Business Consultant | To be started
Technical project Kick-off | Align IT and integration teams on environment setup, SSO, and data migration. | 0 |  |  |  |  | Technical Consultant | To be started
Schedule Weekly cadence | Set up recurring weekly project status meetings | 0 |  |  |  |  | Project Manager | To be started
Update and baseline Project Plan | Finalize and baseline the project plan with updated dates and milestones. | 5 |  |  |  |  | Project Manager | To be started
Share updated Business usecases | Share finalized business workflows and processes for confirmation. | 2 |  |  |  |  | Customer | To be started
Build Prototype on Pilot | Configure initial setup in the Pilot environment based on agreed design. | 2 |  |  |  |  | Business Consultant | To be started
Demo on Pilot | Demonstrate prototype to the client for feedback and approval. | 0 |  |  |  |  | Business Consultant | To be started
Technical Consulting Sessions | Conduct sessions to resolve technical or complex configuration needs. | 0 |  |  |  |  | Technical Consultant | To be started
Sample Data Migration Files | Share sample data templates to test in data. | 2 |  |  |  |  | Technical Consultant | To be started
Review Sample Data Migration Files | Validate sample data with customer for accuracy and completeness. | 2 |  |  |  |  | Customer | To be started
Upload Sample Historical data to the platform | Load reviewed sample data into Pilot for testing. | 2 |  |  |  |  | Technical Consultant | To be started
Admin Training Session 1 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 3 |  |  |  |  | Customer/Business Consultant | To be started
Admin Training Session 2 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 0 |  |  |  |  | Customer/Business Consultant | To be started
Admin Training Session 3 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 0 |  |  |  |  | Customer/Business Consultant | To be started
Admin Training Session 4 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 0 |  |  |  |  | Customer/Business Consultant | To be started
Share sample test scripts | Share draft UAT scripts covering key test scenarios. | 0 |  |  |  |  | Business Consultant | To be started
UAT Kick-off | Start UAT phase; align on scope, roles, and timelines. | 0 |  |  |  |  | Customer/Business Consultant | To be started
UAT- Round 1 | First round of user acceptance testing; record and fix issues. | 0 |  |  |  |  | Customer | To be started
UAT- Round 2 | Retest fixed issues and validate final scenarios. | 0 |  |  |  |  | Customer | To be started
UAT Sign-off | Obtain client approval that testing is complete and successful. | 0 |  |  |  |  | Customer | To be started
Data Migration Pilot signoff | Obtain client approval that data migration is complete and successful. | 2 |  |  |  |  | Customer | To be started
Final Data Migration to Performance 1 | Migrate final validated data to Production. | 5 |  |  |  |  | Technical Consultant | To be started
Signoff Data Migration to Performance | Confirm and approve that final data migration is successful. | 2 |  |  |  |  | Customer | To be started
Production Configuration | Apply any last configuration updates in Production environment. | 3 |  |  |  |  | Customer | To be started
Final Review on Production | Conduct a final validation of Production setup. | 2 |  |  |  |  | Customer | To be started
Go-Live | Launch the system for all users and transition to post-go-live support. | 2 |  |  |  |  | Customer | To be started

## RAID Log
[Customer] Action Items Log |  |  | Last Updated: | 2026-04-08
ID | Date Logged | Specific Description | Risk ¦ Issue ¦ Action ¦ Decision | Status | Priority | Go Live Blocker | Due Date | Closed Date | Owner | Notes

## Timeline (hidden)
[Customer Name]
|  |  |  | September | [21 empty] | October | [30 empty] | November | [29 empty] | December
|  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5
Milestone description | Progress | Start | Days | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Business Proces Alignment | 75% | 2025-10-01 | 3
Learning Management |  | 2026-04-13 | 1
Learning Experience | 50% | 2025-09-28 | 10
Extended Enterprise |  | 2025-10-21 | 1
Guide | 10% | 2025-10-07 | 6
Certifications | 60% | 2025-10-07 | 13
Connect | 50% | 2025-10-09 | 9
Competencies | 33% | 2025-10-14 | 11
SSO |  | 2025-10-16 | 1
Welcome Page Template |  | 2025-10-17 | 24
HDLL |  | 2025-10-16 | 4
MDLL |  | 2025-10-19 | 14
DKIM |  | 2025-11-03 | 6
ODF |  | 2025-11-07 | 3
OSSO |  | 2025-10-07 | 19
Web Services (APIs) |  | 2025-11-10 | 15
Data Connector |  | 2025-11-24 | 5
|  | 2026-01-05 | 1

## Enterprise Timeline (hidden)
| April |  | May |  |  |  | June |  |  | July | [5 empty] | Aug |  |  |  | Sept |  |  |  |  | Oct
| 21-25 | 28-2 | 5-9 | 12-16 | 19-23 | 26-30 | 2-6 | 9-13 | 16-20 | 23-27 | 30-4 | 7-11 | 14-18 | 21-25 | 28-1 | 4-8 | 11-15 | 18-22 | 25-29 | 1-5 | 8-12 | 15-19 | 22-26 | 29-3 | 6-10 | 13-17 | 20-24 | 27-31
Business Process Alignment | April 21-25: BPA Workshops; May 12-16: Deliver BPA Report; May 19-23: Mattress Firm to Review
Inbound Data Feed - OU/Users (IDF) Connector | May 19-23: Configure Pilot; Aug 4-8: Validate Pilot; Aug 18-22: Configure Production; Sept 8-12: Validate Production
Master Data Load - Learning (MDLL) | June 2-6: Configure Pilot; Aug 4-8: Validate Pilot; Aug 18-22: Configure in Production; Sept 1-5: Configure Production; Oct 13-17: Validate Production
Consulting - Single Sign On - Standard (SSO) Connector | May 26-30: Configure in Pilot; July 23-27: Test in Pilot; Sept 1-5: Configure in Production; Sept 15-19: Test in Production; Oct 13-17: Open to Employees
Learning Experience Data Connection – CSX | April 21-25: Configure Connection; May 12-16: Set Filters and Test
Historical Data Load - Learning (HDLL) | Aug 11-15: Files to Pilot and Validate; Sept 15-19: Files to Prod; Sept 29-3: Validate
Cornerstone Learning Experience Enterprise Implementation | April 28-2: Build Prototype; June 2-6: BPA>Imp Transition/ Deliver Prototype; June 9-13: BC on PTO; June 16-20: Design; Sept 8-12: Proof of Concept Prep and Delivery; Sept 22-26: UAT; Oct 13-17: System Go-live Ready; Oct 20-24: Go-Live
Learning Implementation - Enterprise
Competency Management Implementation - Enterprise
Certification Management Implementation - Enterprise
Learning Data Migration SABA | Oct 20-24: Pull Extract
Governance Part B | Sept 22-26: Governance Part B
Optional:
Custom Login Page (CLP) | May 5-9: Configure in Pilot; May 26-30: Validate in Pilot; June 16-20: Configure in Production; July 7-11: Validate in Production
Analytics Plus
Widget Extension
Welcome Page Template Design Package | May 5-9: Configure in Pilot; June 16-20: Validate in Pilot; July 14-18: Configure in Production; Aug 18-22: Validate in Production
Copy Down
Training Update freeze in Saba EOW

## Project Timeline (hidden)
[Customer Name]
|  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2025-05-19 |  |  |  | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May
[5 empty] | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S
[5 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29
Milestone description | Category | Progress | Start | Days
Learn | On Track | 25% | 2025-11-01 | 250
Plan | On Track | 50% | 2025-11-01 | 20
Advise | On Track |  | 2025-11-01 | 21
Design | On Track | 10% | 2025-11-07 | 6
UAT | On Track
Launch | On Track | 60% | 2025-11-07 | 13
Hypercare
Inbound Data Feed | On Track
Pilot | On Track | 30% | 2025-05-19 | 125
Production
SSO | On Track |  | 2025-05-22 | 14
Pilot | On Track |  | 2025-06-06 | 6
Production | On Track |  | 2025-11-07 | 19
MDL | On Track
Pilot | On Track |  |  | 30
Production | On Track
HDL | Low Risk |  | 2025-09-17 | 15
Pilot | On Track
Production | On Track
To add more data, Insert new rows ABOVE this one | On Track
Formulas:
Start = [Start, row above]+15

## Hypercare Log
Hypercare Log | [5 empty] | Hypercare Start Date |  | [enter date] | Hyper Care End Date | [enter date]
HC ID | Date Logged | Logged By | Issue | Description Details | Priority | Go live Impact | Assigned to | Status | Resolution Summary | Resolution Date | Validated By | Next Steps
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38