## Learn-Plan (hidden)
S.No | Task | Pre-Requisite | Duration | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Owner | Status | Session Duration | Session Agenda (Brief) | Comments
1 | Project Kick Off |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | All | Complete |  |  | Will be scheduled if needed
2 | Survey - Questionnaire |  |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-07-10 | CSOD | Complete
3 | Success Centre Access and Trainings Review |  | 5 | 2025-07-10 | 2025-07-17 | 2025-07-10 | 2025-07-17 | ProActive | Complete
4 | Share updated questionnaire | 2 | 8 | 2025-07-11 | 2025-07-23 | 2025-07-10 | 2025-07-23 | ProActive | Complete
5 | Discovery Workshop Session 1 | 4 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | All | Complete | 90 Mins
6 | Discovery Workshop Session 2 |  |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | All | Complete | 90 Mins
7 | Discovery Workshop Session 3 |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | All | Complete | 90 Mins
8 | Discovery Workshop Session 4 |  |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | All | Complete | 90 Mins
9 | Schedule Weekly cadence |  | 2 | 2025-08-26 | 2025-08-28 |  |  | All | Complete
10 | Schedule Steerco Meeting |  | 2 | 2025-08-26 | 2025-08-28 |  |  | All
11 | Prepare Project Plan |  |  | 2025-08-25 | 2025-08-25 |  |  | CSOD | Complete
12 | Review and baseline project Plan |  | 5 | 2025-08-26 | 2025-09-02 |  | 2025-09-15 | All | In-Progress |  |  | Customer wants to fast track. Review is in progress
13 | Share updated usecases |  | 5 | 2025-08-25 | 2025-09-01 |  |  | ProActive | Complete
14 | Share sample test scripts |  |  | 2025-08-25 | 2025-08-25 | 2025-09-02 | 2025-09-02 | CSOD | Complete
15 | Technical project Kick-off |  |  | 2025-08-28 | 2025-08-28 | 2025-09-28 | 2025-09-03 | All | Complete | 120 Mins | The integration consultant will kick off relevant tech project for Cornerstone HR (Edge Import and SSO)
16 | 1. Single Sign-on- Not doing |  | 5 | 2025-08-29 | 2025-09-05 |  |  | All | NA
17 | 2. MS Teams Integration-VILT |  | 5 | 2025-08-29 | 2025-09-05 |  |  | All | NA
18 | 3. MS Teams Integration-LITFOW |  | 5 | 2025-08-29 | 2025-09-05 |  |  | All | NA
19 | 4. Employee and OU -Edge Templates |  | 7 | 2025-08-29 | 2025-09-09 | 2025-08-29 |  | All | In-Progress |  | OU files finalized, Other files to be shared by 18-Sep
20 | 5. Master Data Load Learn-MDLL |  | 10 | 2025-08-29 | 2025-09-12 | 2025-09-04 |  | All | In-Progress
21 | 6. Historic Data Load Learn-HDLL |  | 15 | 2025-08-29 | 2025-09-19 |  |  | All | NA
22 | Technical Consulting Sessions |  | 10 | 2025-08-29 | 2025-09-12 | 2025-09-04 |  | All | In-Progress | 30 Mins | Session to review anything on the 6 technical project items
23 | Sample Employee and OU files |  |  | 2025-09-09 | 2025-09-09 |  |  | ProActive | In-Progress
24 | Sample MDLL files |  |  | 2025-09-12 | 2025-09-12 |  |  | ProActive | In-Progress
25 | Sample HDLL files |  | 5 | 2025-09-15 | 2025-09-22 |  |  | ProActive | NA
26 | Branding Workshop |  |  | 2025-09-10 | 2025-09-10 |  | 2025-09-10 | All | Complete | 60 Mins
27 | Design Sessions covering Content Creator, Certification Management |  |  | 2025-09-02 | 2025-09-11 | 2025-09-02 | 2025-09-11 | All | Complete
28 | Design Session 1 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | All | Complete | 120 Mins | Following the Discovery workshops, the consultant will conduct sessions that explores relevant module settings to determine the desired system behaviour.
29 | Design Session 2 |  |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | All | Complete | 120 Mins
30 | Design Session 3 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | All | Complete | 120 Mins
31 | Share updated usecases |  | 2 | 2025-09-12 | 2025-09-16 | 2025-09-12 | 2025-09-16 | ProActive | Complete |  | Based on the discussions, Usecases document to be updated
32 | Build Prototype on Pilot |  | 3 | 2025-09-03 | 2025-09-08 | 2025-09-03 | 2025-09-08 | CSOD | Complete
33 | Demo on Pilot |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | CSOD | Complete | 120 Mins
34 | Admin Trainings |  | 5 | 2025-09-08 | 2025-09-15 | 2025-09-08 | 2025-09-15 | ProActive | Complete
35 | Production Configuration |  | 6 | 2025-09-16 | 2025-09-24 | 2025-09-16 |  | ProActive | Complete | 120 Mins | Session with Rajesh to review the configurations done by the Pro-active team
36 | Copy Down Pilot-Stage |  | 4 | 2025-09-25 | 2025-10-01 | 2025-09-25 | 2025-10-01 | CSOD | Complete
37 | Copy down Prod to Pilot |  | 3 | 2025-09-25 | 2025-09-30 | 2025-09-25 | 2025-09-30 | CSOD | Complete
3 | Upload data to pilot |  | 2 | 2025-10-01 | 2025-10-03 | 2025-10-01 | 2025-10-03 | ProActive | Complete
39 | UAT Preparation and Test Scripts update |  | 17 | 2025-09-09 | 2025-10-03 | 2025-09-09 | 2025-10-03 | ProActive | Complete
40 | UAT |  | 10 | 2025-10-06 | 2025-10-20 | 2025-10-07 |  | ProActive | In-Progress | 60 Mins | [13-Oct]: Customer requested for UAT sign-off to be extended til 23-Oct to facilitate more time to review regional admin tasks UAT Stand-up Sessions scheduled
41 | UAT Sign-off |  |  | 2025-10-20 | 2025-10-20 |  |  | ProActive
42 | Share final MDLL |  |  | 2025-10-20 | 2025-10-20 |  |  | ProActive
43 | Share final HDLL |  |  | 2025-10-20 | 2025-10-20 |  |  | ProActive
44 | Update Production Configuration |  | 4 | 2025-10-21 | 2025-10-27 |  |  | ProActive
45 | Final Review on Production |  | 3 | 2025-10-28 | 2025-10-31 |  |  | ProActive
46 | Go-Live |  |  | 2025-11-03 | 2025-11-03 |  |  | ProActive
Formulas:
Planned End Date = [Planned Start Date]
Planned End Date = WORKDAY([Planned Start Date],[Duration])
Planned Start Date = WORKDAY([Planned End Date, row above],7)
Planned Start Date = WORKDAY([Planned Start Date, row above],3)

## Performance-Plan
Task | Description | Duration | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Owner | Status | Yes Prep Comments
Performance Implementation | [6 empty] | All | In Progress
Project Kick Off | Officially start the project with all stakeholders; review scope, roles, and timelines. | 0 |  |  |  |  | Project Manager | Completed
Discovery - Questionnaire | Gather initial inputs on current performance processes and expectations. | 0 |  |  |  |  | Project Manager | Completed
Success Centre Access and Trainings Review | Ensure client has access to Cornerstone resources and training materials. | 15 |  |  |  |  | Customer | In Progress
Share updated questionnaire | Customer will complete quiestionnaire and provide any document to help understand current processes and needs | 0 |  |  |  |  | Customer | To be started
Discovery Workshop Session | Discuss business needs and validate requirements for Performance setup. | 0 |  |  |  |  | Business Consultant | To be started
OU Work shop | Organisation Unit Workshop | 0 |  |  |  |  | Business Consultant | To be started
Technical project Kick-off | Align IT and integration teams on environment setup, SSO, and data migration. | 0 |  |  |  |  | Technical Consultant | To be started
Schedule Weekly cadence | Set up recurring weekly project status meetings | 0 |  |  |  |  | Project Manager | To be started
Update and baseline Project Plan | Finalize and baseline the project plan with updated dates and milestones. | 5 |  |  |  |  | Project Manager | To be started
Share updated Business usecases | Share finalized business workflows and processes for confirmation. | 2 |  |  |  |  | Customer | To be started
Build Prototype on Pilot | Configure initial setup in the Pilot environment based on agreed design. | 2 |  |  |  |  | Business Consultant | To be started
Demo on Pilot | Demonstrate prototype to the client for feedback and approval. | 0 |  |  |  |  | Business Consultant | To be started
Technical Consulting Sessions | Conduct sessions to resolve technical or complex configuration needs. | 0 |  |  |  |  | Technical Consultant | To be started
Sample Data Migration Files | Share sample data templates to test in data. | 2 |  |  |  |  | Technical Consultant | To be started
Review Sample Data Migration Files | Validate sample data with customer for accuracy and completeness. | 2 |  |  |  |  | Customer | To be started
Upload Sample Historical data to the platform | Load reviewed sample data into Pilot for testing. | 2 |  |  |  |  | Technical Consultant | To be started
Admin Training Session 1 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 3 |  |  |  |  | Customer/Business Consultant | To be started
Admin Training Session 2 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 0 |  |  |  |  | Customer/Business Consultant | To be started
Admin Training Session 3 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 0 |  |  |  |  | Customer/Business Consultant | To be started
Admin Training Session 4 | Conduct training sessions for client admins covering setup, workflows, performance cycles, reports, and troubleshooting. | 0 |  |  |  |  | Customer/Business Consultant | To be started
Share sample test scripts | Share draft UAT scripts covering key test scenarios. | 0 |  |  |  |  | Business Consultant | To be started
UAT Kick-off | Start UAT phase; align on scope, roles, and timelines. | 0 |  |  |  |  | Customer/Business Consultant | To be started
UAT- Round 1 | First round of user acceptance testing; record and fix issues. | 0 |  |  |  |  | Customer | To be started
UAT- Round 2 | Retest fixed issues and validate final scenarios. | 0 |  |  |  |  | Customer | To be started
UAT Sign-off | Obtain client approval that testing is complete and successful. | 0 |  |  |  |  | Customer | To be started
Data Migration Pilot signoff | Obtain client approval that data migration is complete and successful. | 2 |  |  |  |  | Customer | To be started
Final Data Migration to Performance 1 | Migrate final validated data to Production. | 5 |  |  |  |  | Technical Consultant | To be started
Signoff Data Migration to Performance | Confirm and approve that final data migration is successful. | 2 |  |  |  |  | Customer | To be started
Production Configuration | Apply any last configuration updates in Production environment. | 3 |  |  |  |  | Customer | To be started
Final Review on Production | Conduct a final validation of Production setup. | 2 |  |  |  |  | Customer | To be started
Go-Live | Launch the system for all users and transition to post-go-live support. | 2 |  |  |  |  | Customer | To be started

## Availability (hidden)
Role | Cornerstone | Upcoming Leaves or Holidays
Business Consultant | Sharmila VijayaKumar
Project Manager | Hari Rs | Nov 17-21
Technical Consultant | Yohitha
Role | Munchkin | Upcoming Leaves or Holidays
Project Manager | Rachel Alaysa - Sr Manager, HRBP
Executive Sponsor | Elaine Cameron - Chief People Officer
Technical Lead (Connectors and SSO) | Patrick Sisante - Director, Global IT & Infrastructure
Technical Lead (Connectors and SSO) | Mark Espiritu - Network Security Engineer
Change Management Lead | Rachel Alaysa
Change Management Lead | Elaine Cameron
Business Process Owner(s) | Rachel Alaysa
Business Process Owner(s) | Elaine Cameron
Business Process Owner(s) | Caleb Elledge - HR & TA Assistant (admin support role)